## Jazz Rockers Risk List
|  | Name: | Jazz Rockers | Date: 04/19/09
|  | Team: | Jazz Rockers | Instructor: -
Cycle: 4
[5 empty] | A | J | K | N |  | A | J | K | N |  |  |  |  | Owner | Followup date | Date Resolved
Risk # |  | Type | Condition/Description | Consequence | Impact |  |  |  |  | Probability |  |  |  |  | Total | Mitigation Plan | Status |  |  |  | Notes
1 |  | Technology | Technical constraints, the Jazz platform, are significant. Even identifying which part to use is difficult. | We might not be able to fully refine our software architecture, subsequently impacting the production planning. | 3 | 4 | 5 | 5 | 4.25 | 3 | 5 | 4 | 5 | 4.25 | 18.0625 |  | Duplicate |  |  |  | Refer R23
2 |  | Team | Some of us are thinking of dropping the course. This might cause overload | We have a schedule slippage or the score is reduced. | 5 | 5 | 4 | 5 | 4.75 | 3 | 3 | 4 | 3 | 3.25 | 15.4375 |  | Closed
1 |  | Team | We are facing problems with the Tool setup on the server. This might hinder our timely data collection process. | We review the data late or we do not get to analyze the data we collect. | 4 | 4 | 4 | 4 | 4 | 2 | 3 | 4 | 4 | 3.25 | 13 |  | Closed | Krishnan, Abhishek
3 |  | Team | One member does not have experience in Java. This might make the person to put in extra efforts. | The person overworks or we face the schedule slippage | 2 | 3 | 2 | 3 | 2.5 | 3 | 4 | 3 | 3 | 3.25 | 8.125 |  | Open
17 |  | Teamwork | Lack of commitment has been observed at time among team members. | This may hamper the schedule of the project | 5 | 2 | 5 | 4 | 4 | 4 | 3 | 3 | 5 | 3.75 | 15 |  | Open
10 |  | Process | Not all team members track time accurately. | We might collect unuseful historical data. | 4 | 2 | 4 | 4 | 3.5 | 4 | 1 | 5 | 4 | 3.5 | 12.25 |  | Open
12 |  | Artifacts | We don't have enough standards of our artifcacts. | We might produce incomplete/unsound artifacts. | 4 | 1 | 5 | 4 | 3.5 | 4 | 1 | 4 | 5 | 3.5 | 12.25 |  | Open
16 |  | Estimation | We don't have reliable estimation. | We might be overloaded. | 3 | 3 | 3 | 4 | 3.25 | 3 | 3 | 4 | 4 | 3.5 | 11.375 |  | Open
4 |  | Requirement | We don’t have historical data to use in estimating component size and development time. | It might be difficult to show our client quantitatively what we can do within the time constraints, thereby unable to pinpoint the project scope. | 2 | 1 | 4 | 4 | 2.75 | 3 | 1 | 4 | 3 | 2.75 | 7.5625 |  | Open
2 |  | Technology | One member (the chief architect) leads design of the architecture | We will lose the person most technically competent, and the team might be stuck with the design activity. | 3 | 4 | 5 | 3 | 3.75 | 3 | 2 | 3 | 2 | 2.5 | 9.375 |  | Open
14 |  | Planning | We don't have sound planning as our basis to track our process. | Team milestones might slip between iterations. | 4 | 5 | 4 | 3 | 4 | 3 | 5 | 1 | 3 | 3 | 12 |  | Open
5 |  | Requirement | Scope of the project hasn't been fixed. | We might make our implemenation plan is not feasible. | 2 | 2 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2.75 | 8.25 |  | Open
8 |  | Process | We don't have an effective way of depicting individual progress. | Impact on the schedule | 4 | 2 | 4 | 4 | 3.5 | 4 | 3 | 1 | 4 | 3 | 10.5 |  | Open
6 |  | Requirement | Different levels of understanding of the product exsit between different team members. | We might have conflicts in requirements and design and devleopment decisions. | 3 | 2 | 5 | 2 | 3 | 3 | 2 | 5 | 3 | 3.25 | 9.75 |  | Open
9 |  | Process | We are not capturing our management overhead properly. | We might not know how much time we have (is left) for non-overhead tasks. | 3 | 3 | 3 | 4 | 3.25 | 3 | 4 | 1 | 5 | 3.25 | 10.5625 |  | Open
21 | J | Teamwork | The team lacks historical, statistical data to be used in estimation and decision making. | This could lead to significant errors in estimation - either understimating and not being able to meet the threshold of success, or overestimating (to compensate?) leading to the team committing to less than what they can deliver (and perhaps unintentionally wasting the excess time on non-value-added activities). | 3 | 3 | 3 | 4 | 3.25 | 2 | 3 | 3 | 4 | 3 | 9.75 |  | Open
15 |  | Planning | Not very well defined process for task allocation exists. | We might have tasks being given to wrong people, hence resulting in low productivity | 4 | 2 | 1 | 5 | 3 | 4 | 2 | 1 | 5 | 3 | 9 |  | Open
19 | J | Teamwork | Some part of Jazz/RTC was instable and we were planning on using a newer version |  | 2 | 3 | 3 | 2 | 2.5 | 2 | 3 | 5 | 2 | 3 | 7.5 |  | Open
7 |  | Process | Individual responsibilties are not effectivly mapped to team roles. | Team members might not coordiante and communicate effectivly or have access to relevant information in a timely fashion. | 4 | 2 | 5 | 3 | 3.5 | 2 | 2 | 2 | 3 | 2.25 | 7.875 |  | Open
20 | J | Teamwork | The team has no prior experience in its chosen software development processes (TSPi, augmented in Spring with ACDM when designing the architecture). | Either execessive time could be spent on learning the processes or, if the processes are not learned adequately, the team will in effect be using ad-hoc processes. | 3 | 1 | 3 | 4 | 2.75 | 2 | 1 | 5 | 3 | 2.75 | 7.5625 |  | Open
22 | J | Teamwork | The end users of the GSD tool are in Germany, so we donn't have direct access to them (e.g., to perform contextual inquiries, present prototypes, etc.) | We might not build the right product (an invalid product). | 2 | 2 | 3 | 2 | 2.25 | 2 | 3 | 3 | 2 | 2.5 | 5.625 |  | Open