## defects removed injected
Phase | Defects Injected | Defects Removed
Planning | 0 | 1
Sys Reqts | 12 | 0
Sys Reqts Inspect | 0 | 12
Sys Test Prep | 1 | 0
Sys Design Review | 2 | 2
SW Test Prep | 2 | 3
SW Design | 14 | 0
SW Design Review | 0 | 4
SW Design Inspect | 0 | 8
Design | 2 | 0
Code | 35 | 5
Code Review | 0 | 14
Code Inspect | 0 | 6
Unit Test | 0 | 8
SW Int Test | 0 | 6
Phase | % Phase Yield | % Process Yield
Sys Reqts Review | 0% | 8.33%
Sys Reqts Inspect | 109% | 8.33%
Sys Design Review | 100% | 100%
SW Design Review | 30.8% | 58.1%
SW Design Inspect | 88.9% | 71%
Code Review | 42.4% | 51.5%
Code Inspect | 31.6% | 72.1%
Unit Test | 61.5% | 80.9%
SW Int Test | 120% | 92.6%
Phase | Planned Time | Actual Time
Project Planning and Oversight | 0.49444 | 0.49028
Software Development Environment | 0.45833 | 0.57083
Detailed Planning | 1900-01-01 15:00 | 1900-01-01 10:43
System Requirements Analysis | 0.58333 | 0.49653
System Requirements Inspection | 0.41667 | 0.41597
Software Design | 1899-12-31 01:00 | 0.58264
Software Design Review | 0.16667 | 0.1125
Software Design Inspection | 0.58333 | 0.36111
Code | 1900-01-02 08:25 | 0.96458
Code Review | 1899-12-31 12:22 | 0.28542
Code Inspection | 0.38889 | 0.41042
Unit Test | 1899-12-31 19:41 | 0.43889
Unit Integration | 0.40139 | 0.12986
Postmortem | 0.875 | 0.91042
Total | 1900-01-13 17:17 | 1900-01-07 14:47
Phase | Defects Injected Actual %
System Requirements Analysis | 17.6%
System Test Preparation | 1.47%
System Design Review | 2.94%
Software Test Preparation | 2.94%
Software Design | 20.6%
Detailed Design | 2.94%
Code | 51.5%
Phase | Defects removed Actual %
Detailed Planning | 1.45%
System Requirements Inspection | 17.4%
System Design Review | 2.9%
Software Test Preparation | 4.35%
Software Design Review | 5.8%
Software Design Inspection | 11.6%
Code | 7.25%
Code Review | 20.3%
Code Inspection | 8.7%
Unit Test | 11.6%
Unit Integration | 8.7%
Phase | Time | Estimated Time
Oversight | 706 | 712
Development Env | 822 | 660
Planning | 3523 | 3780
Sys Reqts | 715 | 840
Sys Reqts Inspect | 599 | 600
SW Design | 839 | 1500
SW Design Review | 162 | 240
SW Design Inspect | 520 | 840
Code | 1389 | 4825
Code Review | 411 | 2182
Code Inspect | 591 | 560
Test | 632 | 2621
SW Int Test | 187 | 578
Postmortem | 1311 | 1260
Phase | Time | Estimated Time | Estimation Error | % Error
Oversight | 706 | 712 | 6 | 0.8427
Development Env | 822 | 660 | -162 | -24.5455
Planning | 3523 | 3780 | 257 | 6.7989
Sys Reqts | 715 | 840 | 125 | 14.881
Sys Reqts Inspect | 599 | 600 | 1 | 0.16667
SW Design | 839 | 1500 | 661 | 44.0667
SW Design Review | 162 | 240 | 78 | 32.5
SW Design Inspect | 520 | 840 | 320 | 38.0952
Code | 1389 | 4825 | 3436 | 71.2124
Code Review | 411 | 2182 | 1771 | 81.1641
Code Inspect | 591 | 560 | -31 | -5.5357
Test | 632 | 2621 | 1989 | 75.8871
SW Int Test | 187 | 578 | 391 | 67.6471
Postmortem | 1311 | 1260 | -51 | -4.0476
Artifact | Plan | Actual | Estimation Error | % Error
SRS Pages | 5 | 14 | -9 | -180
STP Pages | 5 | 7 | -2 | -40
SDD Pages | 10 | 16 | -6 | -60
New & Changed LOC | 1260 | 410 | 850 | 67.4603