## Sheet1
Name | Abhishek Minde |  | Date | 2009-04-12
Team | Gang of four |  | Instructor | Mel
Part/Level |  |  | Cycle | 2
Note: We use this document only to document the issues. Risks are only summarized here. And risks are described in the risk document.
Date | Summary | Type | Priority (Liklihood, Impact) | Owner | Followup Date | Resolved | Date Resolved | Notes
2009-04-14 | Sometimes we face problems with VPN. This inhibts us from connecting to the team dashboard. | Issue | HL | Abhishek | 2009-04-14 | Yes | 2009-04-14 | This cannot be solved. However, we make sure that we syncronize process dashboard with team dashboard quite often.
2009-04-15 | We don’t have all documents in the team repository. We have some documents on the google docs. | Issue | HL | Joao | 2009-04-22 | Yes | 2009-04-24
2009-03-23 | Some of us are thinking of dropping the course. This might cause overload | Risk | Please refer to the Risk document
2009-04-04 | We are facing problems with the Tool setup on the server. This might hinder our timely data collection process. | Risk | Please refer to the Risk document
2009-03-28 | One member does not have experience in Java. This might make the person to put in extra efforts. | Risk | Please refer to the Risk document